## _GANTT_C1_Rev__(3)
Overall presentation of activities - Component 1 - Revised 16 November 2015
ID | DESCRIPTION |  | Y 1 | [11 empty] | Y 2 | [11 empty] | Y 3 | [11 empty] | Y 4
|  |  | S 1 | [5 empty] | S 2 | [5 empty] | S 1 | [5 empty] | S 2 | [5 empty] | S 1 | [5 empty] | S 2 | [5 empty] | S 1 | [5 empty] | S 2
|  | M1 | M 2 | M 3 | M 4 | M 5 | M 6 | M 7 | M 8 | M 9 | M 10 | M 11 | M 12 | M 13 | M 14 | M 15 | M 16 | M 17 | M 18 | M 19 | M 20 | M 21 | M 22 | M 23 | M 24 | M 25 | M 26 | M 27 | M 28 | M 29 | M 30 | M 31 | M 32 | M 33 | M 34 | M 35 | M 36 | M 37 | M 38 | M 39 | M 40 | M 41 | M 42 | M 43 | M 44 | M 45 | M 46 | M 47
|  | XII 14 | I 15 | II 15 | III 15 | IV 15 | V 15 | VI 15 | VII 15 | VIII 15 | IX 15 | X 15 | XI 15 | XII 15 | I 16 | II 16 | III 16 | IV 16 | V 16 | VI 16 | VII 16 | VIII 16 | IX 16 | X 16 | XI 16 | XII 16 | I 17 | II 17 | III 17 | IV 17 | V 17 | VI 17 | VII 17 | VIII 17 | IX 17 | X17 | XI 17 | XII 17 | I 18 | II 18 | III 18 | IV 18 | V 18 | VI 18 | VII 18 | VIII 18 | IX 18 | X 18
1 | Component 1 - Strenthening institutional capacity for for social protection policy development and reforms
1.1 | Result 2: Under the leadership of NDRC, coordination of policy making among government agencies in areas related to social protection reform is strengthened
1.1.1 | Social insurance administration systems reform - Contribution to XIIIth 5-Year Plan | S 2 M 8: PD; S 1 M 14: WS/T
1.1.2 | Coordination of policy making among government agencies in areas related to social protection reform | S 2 M 22: HLE
1.2 | Result 3: Capacity of NDRC in policy development and implementation, notably establishing and enforcing a national policy evaluation technique in the area of social protection, is enhanced
1.2.1 | Relationship of pension benefit with minimum social wage | bar: S 1 M 26 to S 2 M 47
1.2.2 | National policy evaluation technique in the area of social protection (indicators, methods and programs) | S 1 M 17: IW; S 2 M 22: HLE
1.3 | Result 4: National policy framework for a full coverage of old-age insurance system throughout China is consolidated by strengthening the interface of various schemes, pension funding pooling, old-age insurance scheme for civil servants/the employee of public agencies and the existing multi-layer pension system
1.3.1 | Pension reform for public sectors | bar: S 2 M 8 to S 1 M 41
1.3.2 | Social pooling of the basic pension component - Evaluation of the combination of basic pension & individual accounts | bar: S 1 M 4 to S 2 M 37
1.3.3 | Universal social pension models | bar: S 1 M 26 to S 2 M 47
1.3.4 | Multi-tiered design of pension systems (public pension, enterprise annuity and individual pension) | S 1 M 7: OT; S 2 M 8: PD; S 1 M 14: WS
1.3.5 | Occupational pension plans for public sectors and private pension plans | bar: S 1 M 26 to S 2 M 47
1.3.6 | Vesting, indexation and adjustment mechanisms of pension benefit | bar: S 1 M 26 to S 2 M 47
1.3.7 | Ageing population and possible strategy of dealing with this situation | S 1 M 19: OT; S 2 M 22: HLE
1.3.8 | Issue related to the informal sector integration in social security schemes | bar: S 1 M 26 to S 2 M 47
1.3.9 | NDC (notional defined contribution) pension reform | bar: S 1 M 26 to S 2 M 47
1.4 | Result 5: Reform efforts in response to urbanization trends, in particular the harmonization/integration of the various basic social protection systems for different groups of beneficiary, the portability of social insurances and better suited assistance schemes
1.4.1 | Improvement of the individual account component in public pension system for urban workers | bar: S 1 M 26 to S 2 M 47
1.4.2 | Relationship between social-economic development and the redistribution function of social security | S 1 M 19: S; S 2 M 22: HLE; S 2 M 23: PS
1.4.3 | Strategy of integrating social security system in urban and rural context also through the portability of social insurances | S 2 M 11: S; S 2 M 12: PD; S 1 M 14: WS /T
LEGENDA
Identification Phase: Situation analysis, Identification and review of possible relevant EU experience, Workshop with Stakeholders on the Identification Phase.
Analysis Phase: Specific analysis of relevant EU experience, Training/visits to EU countries, Workshop with Stakeholders on the Analysis Phase, Elaboration of reform proposal.
Follow-up Phase: Follow-up and ongoing technical assistance and tool development, Training needs analysis and training definition, Possible Training conducted (EU and/or China), Possible pilot application, Evaluation of follow-up phase and lesson learned.
T | In-country training
OT | Overseas training
S | Study visit abroad
PS | Pilot sites study visit abroad
PD | Panel Discussion
WS | Workshop
IW | International Workshop
HLE | High level event
C | Technical consultancy by European expert