## _GANTT_C1_Rev__(4)
Overall presentation of activities - Component 1 - Revised May 2016
ID | DESCRIPTION |  | Y 1 | [11 empty] | Y 2 | [11 empty] | Y 3 | [11 empty] | Y 4
|  |  | S 1 | [5 empty] | S 2 | [5 empty] | S 1 | [5 empty] | S 2 | [5 empty] | S 1 | [5 empty] | S 2 | [5 empty] | S 1 | [5 empty] | S 2
|  | M1 | M 2 | M 3 | M 4 | M 5 | M 6 | M 7 | M 8 | M 9 | M 10 | M 11 | M 12 | M 13 | M 14 | M 15 | M 16 | M 17 | M 18 | M 19 | M 20 | M 21 | M 22 | M 23 | M 24 | M 25 | M 26 | M 27 | M 28 | M 29 | M 30 | M 31 | M 32 | M 33 | M 34 | M 35 | M 36 | M 37 | M 38 | M 39 | M 40 | M 41 | M 42 | M 43 | M 44 | M 45 | M 46 | M 47
|  | XII 14 | I 15 | II 15 | III 15 | IV 15 | V 15 | VI 15 | VII 15 | VIII 15 | IX 15 | X 15 | XI 15 | XII 15 | I 16 | II 16 | III 16 | IV 16 | V 16 | VI 16 | VII 16 | VIII 16 | IX 16 | X 16 | XI 16 | XII 16 | I 17 | II 17 | III 17 | IV 17 | V 17 | VI 17 | VII 17 | VIII 17 | IX 17 | X17 | XI 17 | XII 17 | I 18 | II 18 | III 18 | IV 18 | V 18 | VI 18 | VII 18 | VIII 18 | IX 18 | X 18
1 | Component 1 - Strenthening institutional capacity for for social protection policy development and reforms
1.1 | Result 2: Under the leadership of NDRC, coordination of policy making among government agencies in areas related to social protection reform is strengthened
1.1.1 | Social insurance administration systems reform - Contribution to XIIIth 5-Year Plan | S 2 M 8: PD; S 1 M 14: WS/T
1.1.2 | Coordination of policy making among government agencies in areas related to social protection reform | S 2 M 22: HLE
1.1.3 | Monitoring interaction between employment promotion and social protection policies | S 1 M 17: IW; S 2 M 22: HLE
1.2 | Result 3: Capacity of NDRC in policy development and implementation, notably establishing and enforcing a national policy evaluation technique in the area of social protection, is enhanced
1.2.1 | Relationship of pension benefit with minimum social wage | bar: S 1 M 26 to S 2 M 47
1.2.2 | National policy evaluation technique in the area of social protection (indicators, methods and programs) | S 1 M 29: IW; S 2 M 34: HLE
1.2.3 | Affordability of Pension schemes (contributions and Government subsidies) | S 1 M 17: IW; S 2 M 22: HLE
1.3 | Result 4: National policy framework for a full coverage of old-age insurance system throughout China is consolidated by strengthening the interface of various schemes, pension funding pooling, old-age insurance scheme for civil servants/the employee of public agencies and the existing multi-layer pension system
1.3.1 | Pension reform for public sectors | bar: S 2 M 8 to S 1 M 41
1.3.2 | Social pooling of the basic pension component - Evaluation of the combination of basic pension & individual accounts | bar: S 1 M 4 to S 2 M 37
1.3.3 | Universal social pension models | bar: S 1 M 26 to S 2 M 47
1.3.4 | Multi-tiered design of pension systems (public pension, enterprise annuity and individual pension) | S 1 M 7: OT; S 2 M 8: PD; S 1 M 14: WS
1.3.5 | Occupational pension plans for public sectors and private pension plans | bar: S 1 M 26 to S 2 M 47
1.3.6 | Vesting, indexation and adjustment mechanisms of pension benefit | bar: S 1 M 26 to S 2 M 47
1.3.7 | Ageing population and possible strategy of dealing with this situation | S 1 M 19: OT; S 2 M 22: HLE
1.3.8 | Issue related to the informal sector integration in social security schemes | bar: S 1 M 26 to S 2 M 47
1.3.9 | NDC (notional defined contribution) pension reform | bar: S 1 M 26 to S 2 M 47
1.4 | Result 5: Reform efforts in response to urbanization trends, in particular the harmonization/integration of the various basic social protection systems for different groups of beneficiary, the portability of social insurances and better suited assistance schemes
1.4.1 | Improvement of the individual account component in public pension system for urban workers | bar: S 1 M 26 to S 2 M 47
1.4.2 | Relationship between social-economic development and the redistribution function of social security | S 2 M 22: HLE; S 2 M 23: PS
1.4.3 | Strategy of integrating social security system in urban and rural context also through the portability of social insurances | S 2 M 11: S; S 2 M 12: PD; S 1 M 14: WS; S 1 M 18: T
LEGENDA
Identification Phase: Situation analysis, Identification and review of possible relevant EU experience, Workshop with Stakeholders on the Identification Phase.
Analysis Phase: Specific analysis of relevant EU experience, Training/visits to EU countries, Workshop with Stakeholders on the Analysis Phase, Elaboration of reform proposal.
Follow-up Phase: Follow-up and ongoing technical assistance and tool development, Training needs analysis and training definition, Possible Training conducted (EU and/or China), Possible pilot application, Evaluation of follow-up phase and lesson learned.
T | In-country training
OT | Overseas training
S | Study visit abroad
PS | Pilot sites study visit abroad
PD | Panel Discussion
WS | Workshop
IW | International Workshop
HLE | High level event
C | Technical consultancy by European expert

## DeatailedAP2016
Component 1 - Overall Plan of Activities - March 2015 - February 2017 - Revision May 2016
ID | DESCRIPTION | RESULT | [10 empty] | COUNTRY | INVOLVED ENTITIES | C/H |  | Y 1 | [11 empty] | Y 2 | [11 empty] | Y 3 |  | ID | DESCRIPTION
[17 empty] | S 1 | [5 empty] | S 2 | [5 empty] | S 1 | [5 empty] | S 2 | [5 empty] | S 1
[16 empty] | M 1 | M 2 | M 3 | M 4 | M 5 | M 6 | M 7 | M 8 | M 9 | M 10 | M 11 | M 12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27
|  | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 | R11 |  |  |  | XII 14 | I 15 | II 15 | III 15 | IV 15 | V 15 | VI 15 | VII 15 | VIII 15 | IX 15 | X 15 | XI 15 | XII 15 | I 16 | II 16 | III 16 | IV.16 | V.16 | VI.16 | VII.16 | VIII.16 | IX.16 | X.16 | XI.16 | XII.16 | I.17 | II 17
0.1 | Selection of sub-topics to be covered under specific year | [14 empty] | S 1 M 5: Y1; S 1 M 6: Y1; S 2 M 11: Y2; S 2 M 12: Y2; S 2 M13: Y2; S 2 M23: Y3; S 2 M24: Y3; S 2 M25: Y3 | 0.1 | Selection of sub-topics to be covered under specific year
0.2 | TOR, selection, recruitment CN & European expert | [14 empty] | S 1 M 5: Y1; S 1 M 6: Y1; S 1 M18: Y2; S 1 M19: Y2; S 1 M26: Y3; S 1 M27: Y3 | 0.2 | TOR, selection, recruitment CN & European expert
0.3 | TOR Situation analysis & Best practices under specific sub-topics | [14 empty] | S 1 M 5: Y1; S 1 M 6: Y1; S 1 M18: Y2; S 1 M19: Y2; S 1 M26: Y3; S 1 M27: Y3 | 0.3 | TOR Situation analysis & Best practices under specific sub-topics
1 | Identification Phase | [41 empty] | 1 | Identification Phase | bar: S 1 M 4 to S 2 M13; S 1 M15 to S 2 M22
1.0 | Brief diagnosis, baseline data, audience of project results (macro-activity 0.1) | [41 empty] | 1.0 | Preparation of brief diagnosis, establish baseline data, analysis audience of project results (macro-activity 0.1) | bar: S 1 M 4 to S 1 M 5
1.1. | Situational Analysis | [41 empty] | 1.1. | Situational Analysis | bar: S 1 M 4 to S 1 M 6; S 2 M 8 to S 2 M 10; S 1 M15 to S 1 M17; S 1 M19 to S 2 M22
1.1.1 | In-depth analysis on the topics 1.1.1; 1.3.2; 1.3.4 |  |  |  | R4 | [7 empty] | CHINA | EU MS (RE)/MCS | C | [27 empty] | 1.1.1 | In-depth analysis on the topics 1.1.1; 1.3.2; 1.3.4 | bar: S 1 M 4 to S 1 M 5
1.1.2 | In-depth analysis on the topic 1.3.1; 1.4.3 | [41 empty] | 1.1.2 | In-depth analysis on the topic 1.3.1; 1.4.3 | bar: S 2 M 8 to S 2 M 9
1.1.3 | Preparation of the Situational Analysis Reports for topics 1.1.1; 1.3.2; 1.3.4 |  | R2 | R3 | R4 | R5 | [6 empty] | CHINA | EU MS (RE)/MCS | C | [27 empty] | 1.1.3 | Preparation of the Situational Analysis Reports for topics 1.1.1; 1.3.2; 1.3.4 | bar: S 1 M 6
1.1.4 | Preparation of the Situational Analysis Reports for topics 1.3.1; 1.4.3 | [41 empty] | 1.1.4 | Preparation of the Situational Analysis Reports for topics 1.3.1; 1.4.3 | bar: S 2 M 10
1.1.5 | In-depth analysis topics Year II (1.3.7 Ageing + 1.1.3, 1.2.3 and 1.4.2. related to HLE) | [41 empty] | 1.1.5 | In-depth analysis topics Year II (1.3.7 Ageing + 1.1.3, 1.2.3 and 1.3.6. related to HLE) | bar: S 1 M19 to S 2 M21
1.1.6 | Preparation of the Situation Analysis Reports for topics Year II | [41 empty] | 1.1.6 | Preparation of the Situation Analysis Reports for topics Year II | bar: S 2 M22
1.2 | Identification and review of possible relevant EU experience | [41 empty] | 1.2 | Identification and review of possible relevant EU experience | bar: S 1 M 4 to S 2 M13; S 1 M19 to S 2 M22
1.2.1 | Preparation of General Country Reports (cross topics) |  | R2 | R3 | R4 | R5 | [6 empty] | EU | EU MS | C | [27 empty] | 1.2.1 | Preparation of General Country Reports (cross topics) | bar: S 1 M 4 to S 2 M13; S 1 M19 to S 2 M22
1.2.3 | Involvement of other EU Contries in the research on EU Best Practice on the specific sub-topics |  |  |  | R4 | [7 empty] | EU | EU MS (CC) / Main Chinese stakeholders | C | [27 empty] | 1.2.3 | Involvement of other EU Contries in the research on EU Best Practice on the specific sub-topics | bar: S 1 M 5 to S 2 M13; S 1 M19 to S 2 M22
1.2.3 | Research and preparation of reports on other EU Countries Best Practices on the specific sub-topics |  |  |  | R4 | [7 empty] | Other EU Countries | EU MS | C | [27 empty] | 1.2.3 | Research and preparation of reports on other EU Countries Best Practices on the specific sub-topics | bar: S 1 M 6 to S 2 M13; S 1 M19 to S 2 M22
1.3 | Panel discussions with stakeholders on the Identification Phase | [41 empty] | 1.3 | Panel discussions with stakeholders on the Identification Phase | bar: S 1 M 7 to S 2 M 8; S 2 M 11 to S 2 M 12; S 1 M19 to S 2 M21
1.3.1.1 | Preparation of Panel discussion contents on possible EU Best Practices to apply in China about the specific topics 1.1.1; 1.3.2; 1.3.4 |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.3.1.1 | Preparation of Panel discussion contents on possible EU Best Practices to apply in China about the specific topics 1.1.1; 1.3.2; 1.3.4 | bar: S 1 M 7
1.3.1.2 | Preparation of Panel discussion contents on possible EU Best Practices to apply in China about the specific topics 1.3.1; 1.4.3 | [41 empty] | 1.3.1.2 | Preparation of Panel discussion contents on possible EU Best Practices to apply in China about the specific topics 1.3.1; 1.4.3 | bar: S 2 M 11
1.3.2 | Identification and travels organisation of EU Expert on the topics included in Panel discussion |  | R2 | R3 | R4 | R5 | [6 empty] | EU | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.3.2 | Identification and travels organisation of EU Expert on the topics included in Panel discussion | bar: S 1 M 7; S 2 M 11
1.3.3 | Meetings to share and discuss the EU Best Practices and to select models to be possibly applied in China | R1 | R2 | R3 | R4 | R5 | [6 empty] | CHINA | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.3.3 | Meetings to share and discuss the EU Best Practices and to select models to be possibly applied in China | bar: S 2 M 8; S 2 M 12
1.3.4 | Preparation of reports with the Panel discussion results and sharing with the Main Chinese stakeholders | R1 | R2 | R3 | R4 | R5 | [6 empty] | EU MS/ CHINA | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.3.4 | Preparation of reports with the Panel discussion results and sharing with the Main Chinese stakeholders | bar: S 2 M 8; S 2 M 12
1.3.5 | Preparation and holding of panel discussion, Year 2 | [41 empty] | 1.3.5 | Preparation and holding of panel discussions, Year 2 | bar: S 2 M 8; S 2 M 12; S 1 M19 to S 2 M21
Analisys Phase | Analysis Phase | [41 empty] | Analysis Phase | bar: S 1 M 3 to S 1 M26
1.4 | Specific analysis of relevant EU experience | [41 empty] | 1.4 | Specific analysis of relevant EU experience | bar: S 2 M 9 to S 2 M 10; S 2 M13 to S 1 M14; S 2 M21 to S 2 M22; S 2 M25 to S 1 M26
1.4.1.1 | Technical feasibility of EU MS Best Practices to be introduced in China and preliminary reform proposals about the specific topics 1.1.1, 1.3.2, 1.3.4 |  |  |  | R4 | [7 empty] | CHINA | EU MS(RE)/MCS | C | [27 empty] | 1.4.1.1 | Technical feasibility of EU MS Best Practices to be introduced in China and preliminary reform proposals about the specific topics 1.1.1, 1.3.2, 1.3.4 | bar: S 2 M 9 to S 2 M 10
1.4.1.2 | Technical feasibility of EU MS Best Practices to be introduced in China and preliminary reform proposals about the specific topics 1.3.1, 1.4.3 | [41 empty] | 1.4.1.2 | Technical feasibility of EU MS Best Practices to be introduced in China and preliminary reform proposals about the specific topics 1.3.1, 1.4.3 | bar: S 2 M13 to S 1 M14
1.4.2 | Definition of a first draft of reform proposal |  | R2 | R3 | R4 | R5 | [6 empty] | CHINA | EU MS/MCS | C | [27 empty] | 1.4.2 | Definition of a first draft of reform proposal | bar: S 2 M 10; S 1 M14; S 2 M22; S 1 M26
1.4.3 | Technical feasibility EU Best practices, topics Year 2 | [41 empty] | 1.4.3 | Technical feasibility EU Best practices, topics Year 2 | bar: S 2 M 10; S 1 M14; S 2 M21 to S 2 M22; S 2 M25 to S 1 M26
1.5 | Training/Study Assignments to EU countries | [41 empty] | 1.5 | Training/Study Assignments to EU countries | bar: S 1 M 3 to S 2 M25
1.5.0 | Workshop in Brussels on Public Sector pension reform | [41 empty] | 1.5.0 | Workshop in Brussels on Public Sector pension reform | bar: S 1 M 3
1.5.1 | 2-Weeks training in France on Multitier pension systems (topic 1.3.4) | [41 empty] | 1.5.1 | 3-Weeks training in France on Multitier pension systems (topic 1.3.4) | bar: S 1 M 3 to S 1 M 7
1.5.1.1 | Organisation training in Europe on EU MS Best Practices on topic 1.3.4 (France) |  |  |  | R4 | [7 empty] | EU | EU MS | C | [27 empty] | 1.5.1.1 | Organisation training in Europe on EU MS Best Practices on topic 1.3.4 (France) | bar: S 1 M 3 to S 1 M 6
1.5.1.2 | Travels and logistic organisation of training |  | R2 | R3 | R4 | R5 | [6 empty] | EU | EU MS | C | [27 empty] | 1.5.1.2 | Travels and logistic organisation of training | bar: S 1 M 6
1.5.1.3 | Carrying out of Training | R1 | R2 | R3 | R4 | R5 | [6 empty] | EU | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.5.1.3 | Carrying out of Training | bar: S 1 M 7
1.5.1.4 | Reports on Training in EU and sharing with the Main Chinese stakeholders | R1 | R2 | R3 | R4 | R5 | [6 empty] | EU | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.5.1.4 | Reports on Training in EU and sharing with the Main Chinese stakeholders | bar: S 2 M 8
1.5.2 | 10 days study visit to Spain, Poland, the Czech republic on Migrant workers (topic 1.4.3) | [41 empty] | 1.5.2 | 10 days study visit to Spain, Poland, the Czech republic on Migrant workers (topic 1.4.3) | bar: S 1 M 7 to S 2 M13
1.5.2.1 | Organisation of Visit in Europe on EU MS Best Practices on topic 1.4.3 |  |  |  | R4 | [7 empty] | EU | EU MS | C | [27 empty] | 1.5.2.1 | Organisation of Visit in Europe on EU MS Best Practices on topic 1.4.3 | bar: S 1 M 7 to S 2 M 10
1.5.2.2 | Travels and logistic organisation of visit in Europe on EU MS Best Practices |  | R2 | R3 | R4 | R5 | [6 empty] | EU | EU MS | C | [27 empty] | 1.5.2.2 | Travels and logistic organisation of visit in Europe on EU MS Best Practices | bar: S 2 M 10 to S 2 M 11
1.5.2.3 | Carrying out of Visit in Europe on EU MS Best Practices | R1 | R2 | R3 | R4 | R5 | [6 empty] | EU | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.5.2.3 | Carrying out of Visit in Europe on EU MS Best Practices | bar: S 2 M 11 to S 2 M 12
1.5.2.4 | Reports on Visit in EU and sharing with the Main Chinese stakeholders | R1 | R2 | R3 | R4 | R5 | [6 empty] | EU | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.5.2.4 | Reports on Visit in EU and sharing with the Main Chinese stakeholders | bar: S 2 M13
1.5.3 | 2-weeks training in Spain on the Challenge of old-age society (topic 1.3.7) | [41 empty] | 1.5.3 | 3-weeks training in Spain on the Challenge of old-age society | bar: S 2 M 12 to S 2 M20
1.5.4 | 2-countries Dialogue & Study visit on Employment and Social security systems - topics 1.1.3 and 1.2.3 | [41 empty] | 1.5.4 | 3-countries Dialogue & Study visit on Employment and Social security systems - topics 1.1.3 and 1.2.3 | bar: S 2 M20 to S 1 M26
1.5.5 | Accompany 1.10.7 + visit to a 3rd country ( D) by 2 NDRC HQ officials to prepare for 2017 programme | [41 empty] | 1.5.5 | Accompany 1.9.6 + visit to a 3rd country (F or I) by 2 NDRC HQ officials to prepare for 2017 programme | bar: S 2 M24
1.6 | Worshop with stakeholders on the Analysis Phase | [41 empty] | 1.6 | Worshop with stakeholders on the Analysis Phase | bar: S 2 M 10 to S 2 M13; S 2 M22
1.6.1 | Preparation of Workshop contents on proposals about the specific topics |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.6.1 | Preparation of Workshop contents on proposals about the specific topics | bar: S 2 M 10 to S 2 M 11
1.6.2 | Identification and travel organisation of EU Experts on the topics included in Workshop |  | R2 | R3 | R4 | R5 | [6 empty] | EU | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.6.2 | Identification and travel organisation of EU Experts on the topics included in Workshop | bar: S 2 M 10 to S 2 M 11
1.6.3 | Meeting for discussing the contents previously identified on the on concrete final proposals | R1 | R2 | R3 | R4 | R5 | [6 empty] | CHINA | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.6.3 | Meeting for discussing the contents previously identified on the on concrete final proposals | bar: S 2 M 12 to S 2 M13
1.6.4 | Workshop closing event | R1 | R2 | R3 | R4 | R5 | [6 empty] | CHINA | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.6.4 | Workshop closing event | bar: S 1 M14
1.6.5 | Preparation of a report with the Workshop results and sharing with the Main Chinese stakeholders | R1 | R2 | R3 | R4 | R5 | [6 empty] | EU/ CHINA | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.6.5 | Preparation of a report with the Workshop results and sharing with the Main Chinese stakeholders | bar: S 1 M14 to S 1 M15
1.6.6 | Workshop Year II (same as HLE) | [41 empty] | 1.6.6 | Workshop Year II (same as HLE) | bar: S 2 M22
1.7 | International workshop on employment policies and social security | bar: S 2 M22
1.7.1 | Preparation of Workshop contents on proposals about the specific topics | bar: S 2 M 12 to S 2 M13; S 2 M22
1.7.2 | Identification and travel organisation of EU Experts on the topics included in Workshop | bar: S 1 M14 to S 1 M16; S 2 M22
1.7.3 | Meeting for discussing the contents previously identified on the on concrete final proposals | bar: S 1 M16; S 2 M22
1.7.4 | Holding workshop | bar: S 1 M17; S 2 M22
1.7.5 | Preparation of a report with the Workshop results and sharing with the Main Chinese stakeholders | bar: S 1 M17 to S 1 M18; S 2 M22
1.8 | Elaboration of reform proposals | [41 empty] | 1.7 | Elaboration of reform proposals | bar: S 2 M 11 to S 1 M26
1.8.1 | 1 month EU Expert advise at central and local (Huizhou, SC Pvce) levels - topic 1.4.3 | [41 empty] | 1.7.1 | EU Expert advise at central and local (Huizhou, Luzhou) levels - topic 1.4.3 | bar: S 1 M19 to S 2 M22
1.8.2.1 | Final identification of reform proposals on topics 1.1.1, 1.3.2, 1.3.4 |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS | C | [27 empty] | 1.7.2.1 | Final identification of reform proposals on topics 1.1.1, 1.3.2, 1.3.4 | bar: S 2 M 11 to S 2 M13
1.8.2.2 | Final identification of reform proposals on topics 1.3.1, 1.4.3 | [41 empty] | 1.7.2.2 | Final identification of reform proposals on topics 1.3.1, 1.4.3 | bar: S 2 M13 to S 1 M15
1.8.3 | Final identification of reform proposals on topics Year II | [41 empty] | 1.7.3 | Final identification of reform proposals on topics Year II | bar: S 1 M19 to S 2 M22
1.8.4 | Definition of a detailed plan activities for testing the proposals locally (if requested) and for the following stages |  | R2 | R3 | R4 | R5 | [6 empty] | EU/ CHINA | EU MS | C | [27 empty] | 1.7.4 | Definition of a detailed plan activities for testing the proposals locally (if requested) and for the following stages | bar: S 1 M14 to S 1 M18; S 2 M22 to S 1 M26
1.8.5 | Preparation of the final reform proposal document and sharing with the Main Chinese stakeholders |  | R2 | R3 | R4 | R5 | [6 empty] | EU/ CHINA | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.7.5 | Preparation of the final reform proposal document and sharing with the Main Chinese stakeholders | bar: S 1 M15 to S 1 M18; S 2 M23 to S 1 M26
Follow Up Phase | [42 empty] | Follow Up Phase | bar: S 2 M 10 to S 1 M27
1.9 | Technical assistance and Tool development, training needs analysis with special reference to topics 1.1.1 and 1.4.3 | [41 empty] | 1.8 | Technical assistance and Tool development, training needs analysis with special reference to topics 1.1.1 and 1.4.3 | bar: S 2 M 10 to S 1 M27
1.10 | Pilot activities | [41 empty] | 1.9 | Pilot activities
1.10.1 | Visit to pilot sites to prepare activity programmes | [41 empty] | 1.9.1 | Visit to pilot sites to prepare activity programmes | bar: S 2 M 10; S 1 M15
1.10.2 | Detailed analysis, Huizhou city | [41 empty] | 1.9.2 | Detailed analysis, Huizhou city | bar: S 2 M 12 to S 1 M14
1.10.3 | Training activities in GD and SC Provinces (IT, management, vesting & portability) |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS | C | [27 empty] | 1.9.3 | Training activities in GD and SC Provinces (IT, management, vesting & portability) | bar: S 1 M17
1.10.4. | Mission to GD and SC, EU expert on Migrant workers questions | [41 empty] | 1.9.4. | Mission to GD and SC, EU expert on Migrant workers questions | bar: S 1 M19 to S 2 M21
1.10.5. | Training activities abroad, pilot sites |  | R2 | R3 | R4 | R5 | [6 empty] | EU/ CHINA | EU MS | C | [27 empty] | 1.9.5. | Training activities abroad, pilot sites | bar: S 2 M22 to S 2 M25
1.10.6 | Reporting on pilot activities to other stakeholders |  | R2 | R3 | R4 | R5 | [6 empty] | EU/ CHINA | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.9.6 | Reporting on pilot activities to other stakeholders | bar: S 1 M15; S 1 M26
1.10.7 | 10-days Study visit Czech Republic and Belgium for Provincial officials on improvements of social security management under conditions of economic and social transition (design, contributions levels, procedures and portability, administrative agencies) - topics 1.1.1, 1.2.3., 1.4.3 | [41 empty] | 1.9.7 | 10-days Study visit Czech Republic and Belgium for Provincial officials on improvements of social security management under conditions of economic and social transition (design, contributions levels, procedures and portability, administrative agencies) - topics 1.1.1, 1.2.3, 1.4.3 | bar: S 2 M24
Horizontal macro activities | [42 empty] | Horizontal macro activities | bar: S 2 M 10 to S 2 M24; S 1 M27
1.11 | 2016 High Level Event on more balanced and sustainable employment and social security policies | [41 empty] | 1.10 | 2016 High Level Event on more balanced and sustainable employment and social security policies | bar: S 2 M 10 to S 2 M23
1.11.1 | Choose topic for high level event | [41 empty] | 1.10.1 | Choose topic for high level event | bar: S 2 M 10
1.11.2 | Prepare programme, choose venue, arrange logistics for HLE |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS | C | [27 empty] | 1.10.2 | Prepare programme, choose venue, arrange logistics for HLE | bar: S 2 M 11 to S 2 M22
1.11.3. | Select reporters and researchers, conduct research | [41 empty] | 1.10.3. | Select reporters and researchers, conduct research | bar: S 1 M14 to S 2 M22
1.11.4. | Prepare visibility activities related to HLE |  | R2 | R3 | R4 | R5 | [6 empty] | EU/ CHINA | EU MS | C | [27 empty] | 1.10.4. | Prepare visibility activities related to HLE | bar: S 1 M15 to S 2 M22
1.11.5 | Hold HLE, report to all stakeholders |  | R2 | R3 | R4 | R5 | [6 empty] | EU/ CHINA | EU MS/ Main Chinese stakeholders | C | [27 empty] | 1.10.5 | Hold HLE, report to all stakeholders | bar: S 2 M22 to S 2 M23
1.12 | Reporting and Evaluation | [41 empty] | 1.11 | Reporting and Evaluation | bar: S 1 M 5 to S 1 M 6; S 2 M 11 to S 2 M 12; S 1 M14; S 1 M18; S 2 M22; S 2 M24; S 1 M27
1.12.1 | EU Results-oriented mission | [41 empty] | 1.11.1 | EU Results-oriented mission | bar: S 2 M 11
1.12.2 | Component reports | [41 empty] | 1.11.2 | Component reports | bar: S 1 M 6; S 2 M 12; S 1 M18; S 2 M24
1.13 | PAC meetings |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS | C | [27 empty] | 1.12 | PAC meetings | bar: S 1 M 5; S 1 M16 to S 1 M17; S 2 M22; S 1 M27
Topics: 1.1.1-Social insurance administration systems reform (Preparation of the XIIIth Five-years Plan); 1.1.2-Coordination of policy making among government agencies in areas related to social protection reform; 1.1.3 （new）Monitoring interaction between employment promotion and social protection policies； 1.2.1-Relationship of pension benefit with minimum social wage; 1.2.2-National policy evaluation technique in the area of social protection (indicators, methods and programs); 1.2.3 (new) - Affordability of Pension schemes (contributions and Government subsidies) - 1.3.1-Pension reform for public sectors; 1.3.2-Social pooling of the basic pension component (Combination of basic pension and individual accounts); 1.3.3-Universal social pension models;1.3.4-Multi-tiered design of pension systems (public pension, enterprise annuity and individual pension); 1.3.5-Occupational pension plans for public sectors and private pension plans; 1.3.6-Vesting, indexation and adjustment mechanisms of pension benefit; 1.3.7-Ageing population and possible strategy of dealing with this situation; 1.3.8-Issue related to the informal sector integration in social security schemes; 1.3.9-NDC (notional defined contribution) pension reform; 1.4.1-Improvement of the individual account component in public pension system for urban workers; 1.4.2-Relationship between social-economic development and the redistribution function of social security; 1.4.3-Strategy of integrating social security system in urban and rural context also through the portability of social insurances.
| 2015 Topic | [14 empty] | S 1 M 2: 2016 Topic

## deliverables
c1 - 2016 activity plan - inputs and deliverables
Topic # | Activity item | Input | Deadline semi-final draft | Best practices | Output | Final Use | Date
1.1.1 | Social insurance management reform | Existing documentation | - | - | Training & Briefing materials | Provincial training course | 1st/2nd Quarter 2016
[6 empty] | Provincial Study visit | October 2016
1.1.3 | Sit. Analysis Monitoring interaction between employment promotion and social protection policies | CN Expert | April | Yes | Report | International workshop - ppts | April 2016
[6 empty] | High Level Event | September 2016
| Research Interaction between employment promotion and social protection policies in Europe | Academic study | April | - | Report | International workshop | April 2016
[6 empty] | High Level Event | September 2016
1.2.3 | Sit. Analysis Sustainability of pension schemes (contributions and government subsidies) | CN Expert | July | Yes | Report | High Level Event | September 2016
[6 empty] | Provincial Study Visit | October 2016
[6 empty] | Dialogue & Study Visit | 2nd half 2016
1.3.7 | Sit. Analysis Ageing population and possible strategy of dealing with this situation | Visit SH Pilot | 1st Q.2016 | - | Input into Sp.Training | 2-weeks training, Spain | June 2016
|  | CN Expert | June | Yes | Report
1.4.2 | Sit. Analysis Relationship between social-economic development and the redistribution function of social security | CN Expert | July | Yes | Report | High Level Event | September 2016
1.4.3 | Strategy of integrating social security system in urban and rural context also through the portability of social insurances | EU Expert | - | - | Report | Consultancy Vesting & Portability | 1st Quarter 2016
[5 empty] | Training material | Provincial training | 1st Quarter 2016
|  | Existing documentation |  |  | Briefing material | Provincial study visit | October 2016
| Policy dialogue & Intern. Workshop on Employment and Social security | 2 EU Experts + 1 High level + Expertise France rep. + 2 High level officials from EC | April | - | Power points | High Level Event | April 2016
| High Level Event 2016-2020 Perspectives for Employment policies and Social security reform | Up to 8 EU experts + Consortium representatives | July | - | Reports/ppts |  | September 2016

## HRC1Y2
C1 - HUMAN RESOURCES - ACTIVITY PLAN 2016 - REVISED MAY 2016
w/d total |  |  |  | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | Total | Balance Yr2 | Activities
Used Y.1 | Years 2 to 4 | Year 2
386 | 945 | 370 | C1 Chinese expert staff | [12 empty] | 326 | 44
91 |  | 120 | Main Chinese expert 1 Zhang Guoqing |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 110 | 10
55 |  | 75 | Main Chinese expert 2 Fang Lianquan |  | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 71 | 4
|  |  | CN EXPERT AGEING | [5 empty] | 20 | 5 | [5 empty] | 25 |  | AR* 1.3.7 (Ageing)
|  |  | CN EXPERT PORTABLILITY (CTD) | [9 empty] | 10 | 10 |  | 20 |  | Technical cooperation 1.4.3 (Migrant Workers)
|  |  | CN EXPERT EMPLOYMENT | [6 empty] | 20 | [5 empty] | 20 |  | AR* 1.1.3 Employment & Social security
|  |  | CN EXPERT AFFORDABILITY | [5 empty] | 20 | 10 | [5 empty] | 30 |  | AR* 1.2.3 (Affordability)
|  |  | CN EXPERT REDISTRIBUTION | [5 empty] | 20 | 10 | [5 empty] | 30 |  | AR* 1.4.2 (Eco.dev.& Redistribution)
|  |  | CN EXPERTS DIALOGUE&WKSHOP |  |  |  | 10 | [10 empty] | 1.1.3 Intern.wkshop on SS and Employment
|  |  | CN EXPERTs - HLE | [8 empty] | 20 |  |  |  | 20 |  | *AR= Assessment Report
240 |  | 175 | Total other C1 CN experts | [12 empty] | 145 | 30
54 |  | 100 | Component assistant | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 12 | 8 | 8 | 8 | 100 | 0
195 | 583.3333 | 200 | Resident expert C1 JV Gruat | 17 | 18 | 23 | 15 | 20 | 15 | 17 | 5 | 20 | 20 | 20 | 10 | 200 | 0
30 | 530 | 180 | C1 EU Public sector staff+Subcontracting
|  |  | EU Expert Employment dialogue |  |  |  | 10 | [8 empty] | 10 |  | Keynote speaker, Employment dialogue 1.1.3
|  |  | EU Expert 1 | [6 empty] | 20 | [5 empty] | 20 |  | Best practices Ageing 1.3.7
|  |  | EU Expert 2 | [6 empty] | 15 |  | 5 |  |  |  | 20 |  | Best practices Affordability & Sustainability 1.2.3, 1.4.2
|  |  | EU Experts 3 |  | 10 | 10 | [9 empty] | 20 |  | Migrant workers 1.4.3
|  |  | EU Experts 4 TO 6 |  |  |  | 15 | [8 empty] | 15 |  | Experts, Employment dialogue (3)
|  |  | EU Experts 7 TO 14 | [8 empty] | 40 |  |  |  | 40 |  | Experts, HLE (8)
|  |  | EU Experts 14 TO 16 | [5 empty] | 15 | [6 empty] | 15 |  | Training, Ageing (3)
|  |  | EU Experts 17 AND 18 | [5 empty] | 6 | [8 empty] | Provincial training Foshan
|  |  | Total 1 EU Public sector staff | [12 empty] | 140 | 40