## ANNEX 8
Overall presentation of activities - Component 1 - Revised November 2016
ID | DESCRIPTION |  | Y 1 | [11 empty] | Y 2 | [11 empty] | Y 3 | [11 empty] | Y 4
|  |  | S 1 | [5 empty] | S 2 | [5 empty] | S 1 | [5 empty] | S 2 | [5 empty] | S 1 | [5 empty] | S 2 | [5 empty] | S 1 | [5 empty] | S 2
|  | M1 | M 2 | M 3 | M 4 | M 5 | M 6 | M 7 | M 8 | M 9 | M 10 | M 11 | M 12 | M 13 | M 14 | M 15 | M 16 | M 17 | M 18 | M 19 | M 20 | M 21 | M 22 | M 23 | M 24 | M 25 | M 26 | M 27 | M 28 | M 29 | M 30 | M 31 | M 32 | M 33 | M 34 | M 35 | M 36 | M 37 | M 38 | M 39 | M 40 | M 41 | M 42 | M 43 | M 44 | M 45 | M 46 | M 47
|  | XII 14 | I 15 | II 15 | III 15 | IV 15 | V 15 | VI 15 | VII 15 | VIII 15 | IX 15 | X 15 | XI 15 | XII 15 | I 16 | II 16 | III 16 | IV 16 | V 16 | VI 16 | VII 16 | VIII 16 | IX 16 | X 16 | XI 16 | XII 16 | I 17 | II 17 | III 17 | IV 17 | V 17 | VI 17 | VII 17 | VIII 17 | IX 17 | X 17 | XI 17 | XII 17 | I 18 | II 18 | III 18 | IV 18 | V 18 | VI 18 | VII 18 | VIII 18 | IX 18 | X 18
1 | Component 1 - Strenthening institutional capacity for for social protection policy development and reforms
1.1 | Result 2: Under the leadership of NDRC, coordination of policy making among government agencies in areas related to social protection reform is strengthened
1.1.1 | Social insurance administration systems reform - Contribution to XIIIth 5-Year Plan | S 2 M 8: PD; S 1 M 14: WS/T; S 2 M 23: PS; S 1 M 27: T; S 1 M 43: TP; S 2 M 44: TP
1.1.2 | Coordination of policy making among government agencies in areas related to social protection reform | S 2 M 22: HLE; S 2 M 34: PD
1.1.3 | Monitoring interaction between employment promotion and social protection policies | S 1 M 17: IW; S 2 M 22: HLE; S 1 M 29: S; S 2 M 36: IW; S 1 M 43: PD; S 2 M 44: S; S 2 M 46: OT
1.2 | Result 3: Capacity of NDRC in policy development and implementation, notably establishing and enforcing a national policy evaluation technique in the area of social protection, is enhanced
1.2.1 | Relationship of pension benefit with minimum social wage | bar: S 1 M 26 to S 2 M 47
1.2.2 | National policy evaluation technique in the area of social protection (indicators, methods and programs) | bar: S 1 M 26 to S 2 M 47
1.2.3 | Affordability of Pension schemes (contributions and Government subsidies) | S 1 M 17: IW; S 2 M 22: HLE; S 1 M 43: PD
1.2.4 | Gender considerations in pension schemes (provisional title) | S 2 M 35: S; S 1 M 40: PD; S 2 M 47: WS
1.3 | Result 4: National policy framework for a full coverage of old-age insurance system throughout China is consolidated by strengthening the interface of various schemes, pension funding pooling, old-age insurance scheme for civil servants/the employee of public agencies and the existing multi-layer pension system
1.3.1 | Pension reform for public sectors | bar: S 2 M 8 to S 2 M 47
1.3.2 | Social pooling of the basic pension component - Evaluation of the combination of basic pension & individual accounts | bar: S 1 M 4 to S 2 M 47
1.3.3 | Universal social pension models | bar: S 1 M 38 to S 2 M 47
1.3.4 | Multi-tiered design of pension systems (public pension, enterprise annuity and individual pension) | S 1 M 7: OT; S 2 M 8: PD; S 1 M 14: WS
1.3.5 | Occupational pension plans for public sectors and private pension plans | bar: S 1 M 38 to S 2 M 47
1.3.6 | Vesting, indexation and adjustment mechanisms of pension benefit | bar: S 1 M 26 to S 2 M 47
1.3.7 | Ageing population and possible strategy of dealing with this situation | S 1 M 19: OT; S 2 M 22: HLE; S 2 M 47: PS
1.3.8 | Issue related to the informal sector integration in social security schemes | S 2 M 44: PD; S 2 M 45: IW/S
1.3.9 | NDC (notional defined contribution) pension reform | bar: S 1 M 26 to S 2 M 47
1.4 | Result 5: Reform efforts in response to urbanization trends, in particular the harmonization/integration of the various basic social protection systems for different groups of beneficiaries, the portability of social insurances and better suited assistance schemes
1.4.1 | Improvement of the individual account component in public pension system for urban workers | bar: S 1 M 26 to S 2 M 47
1.4.2 | Relationship between social-economic development and the redistribution function of social security | S 2 M 22: HLE; S 2 M 34: PD; S 2 M 35: IW; S 2 M 36: SV
1.4.3 | Strategy of integrating social security system in urban and rural context also through the portability of social insurances | S 2 M 11: S; S 2 M 12: PD; S 1 M 14: WS; S 1 M 17: T; S 2 M 23: PS; S 1 M 27: T; S 2 M 44: WS
LEGENDA
Identification Phase: Situation analysis, Identification and review of possible relevant EU experience, Workshop with Stakeholders on the Identification Phase.
Analysis Phase: Specific analysis of relevant EU experience, Training/visits to EU countries, Workshop with Stakeholders on the Analysis Phase, Elaboration of reform proposal.
Follow-up Phase: Follow-up and ongoing technical assistance and tool development, Training needs analysis and training definition, Possible Training conducted (EU and/or China), Possible pilot application, Evaluation of follow-up phase and lesson learned.
T | In-country training | M1: PD; S 1 M 3: Panel Discussion
OT | Overseas training | M1: WS; S 1 M 3: Workshop
S | Study visit abroad | M1: IW; S 1 M 3: International Workshop
PS | Pilot sites study visit abroad | M1: HLE; S 1 M 3: High level event
TP | Technical cooperation, pilot sites | M1: C; S 1 M 3: Technical consultancy by European expert

## ANNEX 7
Component 1 - Overall Plan of Activities - November 2017 - November 2018
ID | DESCRIPTION | RESULT | [10 empty] | COUNTRY | INVOLVED ENTITIES | C/H | Y2 |  | Y3 |  | Y4 | [13 empty] | Y 4 |  | ID
[20 empty] | S1 | [5 empty] | S2 | [7 empty] | S 1
[16 empty] | M 24 | M25 | M36 | M37 | M38 | M39 | M40 | M41 | M42 | M43 | M44 | M45 | M46 | M47 | M48 | M35 | M36 | M37 | M38 | M39
|  | R1 | R2 | R3 | R4 | R5 | R6 | R7 | R8 | R9 | R10 | R11 |  |  |  | XI 16 | XII 16 | XI 17 | XII 17 | I 18 | II.18 | III.18 | IV.18 | V.18 | VI.18 | VII.18 | VIII.18 | IX.18 | X.18 | XI.18 | X.17 | XI.17 | XII.17 | I.18 | II 18
0.1 | Selection of sub-topics to be covered under specific year | [34 empty] | 0.1 | bar: M 24 to M37; S2 M35 to S2 M37
0.2 | TOR, selection, recruitment CN & European expert | [34 empty] | 0.2 | bar: M 24 to M25; M37 to S1 M39; S 1 M38 to S 1 M39
0.3 | TOR Situation analysis & Best practices under specific sub-topics | [34 empty] | 0.3 | bar: M 24 to M25; M37 to S1 M39; S 1 M38 to S 1 M39
1 | Identification Phase | [34 empty] | 1
1.1. | Situational Analysis | [34 empty] | 1.1.
1.1.1 | In-depth analysis on topic 1.1.3 (Vocational training)
1.1.2 | In-depth analysis on the topics 1.1.3,1.2.3,1.3.5 (Social security and other redistribution regulations and policy tools ) |  |  |  | R4 | [7 empty] | CHINA | EU MS (RE)/MCS | C | [20 empty] | 1.1.1 | bar: M25 to S2 M45
1.1.3 | In-depth analysis for topics 1.3.3, 1.4.3 (universal income) | bar: M37 to S2 M44
1.1.4 | In-depth analysis for topic 1.3.8 (informal sector integration) | bar: M37 to S2 M45
1.1.5 | In-depth analysis on the topic 1.2.4 (gender considerations) | bar: S1 M41 to S2 M37
1.2 | Identification and review of possible relevant EU experience | [34 empty] | 1.2
1.2.1 | Preparation of Country Reports on the topics 1.1.3, 1.3.5, 1.3.8 |  | R2 | R3 | R4 | R5 | [6 empty] | EU | EU MS | C | [20 empty] | 1.2.1 | bar: M25 to M37
1.2.2 | Preparation of Country Reports on the topic 1.2.4 |  |  |  | R4 | [7 empty] | EU | EU MS (CC) / Main Chinese stakeholders | C | [20 empty] | 1.2.3 | bar: S2 M36 to S 1 M39
1.3 | Panel discussions with stakeholders on the Identification Phase | [34 empty] | 1.3
1.3.1 | Panel discussion on topics 1.1.3, 1.3.5, 1.3.8 |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS/ Main Chinese stakeholders | C | [20 empty] | 1.3.1.1 | bar: S2 M44; S2 M35 to S2 M36
1.3.2 | Panel discussion / International workshop on topic 1.2.4 |  | R2 | R3 | R4 | R5 | [6 empty] | EU | EU MS/ Main Chinese stakeholders | C | [20 empty] | 1.3.2 | bar: S 1 M39
Analisys Phase | Analysis Phase | [34 empty] | Analysis Phase
1.4 | Specific analysis of relevant EU experience | [34 empty] | 1.4
1.4.1 | European research report on the topic 1.2.4 (gender considerations) | bar: S1 M39 to S2 M46; S2 M35 to S2 M37
1.4.2 | Technical feasibility of EU MS Best Practices to be introduced in China and preliminary reform proposals about the specific topics |  |  |  | R4 | [7 empty] | CHINA | EU MS(RE)/MCS | C | [20 empty] | 1.4.1.1 | bar: M25 to S2 M46; S 1 M38 to S 1 M39
1.4.3 | Definition of a first draft of reform proposal |  | R2 | R3 | R4 | R5 | [6 empty] | CHINA | EU MS/MCS | C | [20 empty] | 1.4.2 | bar: S2 M46 to S2 M47; S 1 M39
1.5 | Training/Study Assignments to EU countries | [34 empty] | 1.5
1.5.0 | 2-Weeks training on Monitoring interaction between Employment and Social security policies (topic 1.1.3) (carried over from 2017) | [34 empty] | 1.5.1 | bar: S1 M38
1.5.1 | 2-weeks training on | bar: S2 M46 to S2 M47
1.5.2 | NDRC vice-chairman visit to EC, Spain | bar: S1 M41
1.5.2 | 8 days study visit on issues related to informal sector integration in social security schemes (topic 1.3.8) | [34 empty] | 1.5.2 | bar: S2 M44; S2 M35
1.6 | Worshop with stakeholders on the Analysis Phase | [34 empty] | 1.6
1.6.1 | Seminar on Active LabourMarket Policies | bar: M36
1.6.2 | Seminar on Gender considerations in pension reform | bar: S2 M47
1.6.3 | International workshop on issues related to informal sector integration into social security schemes (topic 1.3.8) |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS/ Main Chinese stakeholders | C | [20 empty] | 1.6.1 | bar: S2 M47; S2 M35
1.7 | Elaboration of reform proposals | [34 empty] | 1.7
1.7.1 | Final identification of reform proposals on topics 1.1.3,1.3.5,1.3.8 |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS | C | [20 empty] | 1.7.2.1 | bar: S2 M46
1.7.2 | Final identification of reform proposals on topic 1.2.4 | bar: S2 M47
Follow Up Phase | [35 empty] | Follow Up Phase
1.8 | Pilot activities | [34 empty] | 1.9
1.8.1 | Cooperation on Statistics management, Guangdong | bar: S1 M43 to S2 M44
1.8.2 | Cooperation on awareness raising on the importance of SS, Qingyuan | bar: S1 M43 to S2 M44
1.8.3 | Research report on long term care, Shanghai | bar: S2 M44
1.8.4 | SH overseas Provincial study visit on ageing | [34 empty] | 1.9.1 | bar: S2 M47
Horizontal macro activities | [35 empty] | Horizontal macro activities
1.9 | Coordination meeting in Italy | [34 empty] | 1.10 | bar: M37; S2 M36
1.1 | Reporting and Evaluation | [34 empty] | 1.11
1.10.1 | Component reports | [34 empty] | 1.11.2 | bar: M 24; M36; S1 M42; S2 M48; S2 M36
1.11 | PAC meetings |  |  |  | R4 | [7 empty] | EU/ CHINA | EU MS | C | [20 empty] | 1.12 | bar: S1 M39; S2 M36
Topics: 1.1.1-Social insurance administration systems reform (Preparation of the XIIIth Five-years Plan); 1.1.2-Coordination of policy making among government agencies in areas related to social protection reform; 1.1.3 Monitoring interaction between employment promotion and social protection policies； 1.2.1-Relationship of pension benefit with minimum social wage; 1.2.2-National policy evaluation technique in the area of social protection (indicators, methods and programs); 1.2.3 - Affordability of Pension schemes (contributions and Government subsidies); 1.2.4 (new) Gender considerations in pension schemes - 1.3.1-Pension reform for public sectors; 1.3.2-Social pooling of the basic pension component (Combination of basic pension and individual accounts); 1.3.3-Universal social pension models;1.3.4-Multi-tiered design of pension systems (public pension, enterprise annuity and individual pension); 1.3.5-Occupational pension plans for public sectors and private pension plans; 1.3.6-Vesting, indexation and adjustment mechanisms of pension benefit; 1.3.7-Ageing population and possible strategy of dealing with this situation; 1.3.8-Issue related to the informal sector integration in social security schemes; 1.3.9-NDC (notional defined contribution) pension reform; 1.4.1-Improvement of the individual account component in public pension system for urban workers; 1.4.2-Relationship between social-economic development and the redistribution function of social security; 1.4.3-Strategy of integrating social security system in urban and rural context also through the portability of social insurances.
Topic introduced in 2018
Previous years'topics

## ANNEX 10
SPRP_3^ Year_Dashboard_C1 17 Nov 2016 - 30 September 2017
C | R | Topic |  | Activity | HR # | [7 empty] | Planned Date |  | Actual Date of conclusion |  |  |  | Mitigation, if delayed | Output |  |  | Notes
|  | ID | Title |  | STE CN# | STE CN names | STE EU# | STE EU names | NDRC | MoF | MoCA | CONS | first step | second step | first step | status | second step | status |  | Type | Submitted | On website
1 | R2 | 1.1.1 | Social insurance administration systems reform – Contribution to the 13th Five-Years Plan | Pilot sites - Provincial Exchange in Shanghai and Guangdong |  |  | 2 | Vleminckx, Tretyak | 4 |  |  | 3 | 2017-02-01 | - | 2017-02-01 | Completed | - | - |  | Mission report | Yes | Yes | Submitted to NDRC and Provinces for use in 2018 activities
|  | 1.1.2 | Coordination of policy making among government agencies in areas related to social protection reform | Technical Notes - European best practices | [8 empty] | 2017-12-01 |  | 2017-09-01 | Completed |  |  |  | Technical Notes | Yes | Yes | Chinese version under linguisitic revision. Expected printed output
|  | 1.1.3 | Monitoring interaction between employment promotion and social protection policies | 2nd High level EU-China Policy dialogue | 3 | Li Kang, Li Shi, Zhou Hong | 4 | Kauffman, Vleminckx, Scarpetta, Kiviniemi | 4 |  |  | 1 | 2017-09-01 |  | 2017-09-01 | Completed |  |  |  | Session report | Yes | Yes | Also directly contributes to R.1
|  |  |  | Ministerial visit to Belgium, Spain and Italy |  |  |  |  | 4 |  |  | 2 | 2017-04-01 | - | 2017-07-07 | Completed | - | - | Took place in July - Not vice-chairman but Director General | Mission report | Yes | Yes
|  |  |  | Workshop on Active Labour Market Policies | 1 | Jing Chao | 5 | Vleminckx, Verhuysse, Sacchi, Ueve, Gauvin | 3 | 1 |  | 5 | 2017-11-01 |  |  | On-going |  |  |  | Session report | No | No | Subject to confirmation
| R3 | 1.2.2 | National policy evaluation technique in the area of social protection (indicators, methods and programs) | Situational analysis | 2 | Zheng Gongchen, Yue Jinglun | [6 empty] | 2017-06-17 |  | 2017-06-30 | Completed | 2017-09-30 | Completed |  | PPTs and Assessment reports | Yes | No | Linked to Training in Germany
|  |  |  | Panel discussion with stakeholders on the Identification phase |  |  |  |  | 20 |  |  |  | 2017-09-30 | - | 2017-09-30 | Completed | - | - |  | Panel Discussion Report | Yes | Yes
|  |  |  | Training in Germany |  |  | 14 | Weber | 20 |  |  | 1 | 2017-06-17 |  |  | Not started | - | - | JGU Mayenz to take over | Compendium of support material, Training Report, Evaluation report of the training course | No | No | Activity now scheduled for January 2018
|  | 1.2.4 | Gender considerations in pension schemes | Situational analysis | 2 | Lin Yi - Sichuan Yue Jinglun - Guangdong | 1 | [5 empty] | 2017-09-30 | 2018 |  | On-going |  |  |  | Assessment report | Yes | No | Reports received from both SC and GD. Follow up part of proposed 2018 plan of activities
|  |  |  | Dialogue and Study visit to Romania |  |  |  |  | 6 |  |  |  | 2017-10-31 | - |  | Delated | - | - |  | Mission report | No | No | Activity frozen for time being
|  |  |  | Panel discussion with stakeholders on the Identification phase | 2 |  | 2 |  | 20 |  |  |  | July 2018 | - |  | Not started | - | - |  | Panel Discussion Report | No | No | 2018
| R4 | 1.3.6 | Parametric reforms of pension system (Vesting, indexation, adjustment mechanisms of pension benefit, benefit formula etc.) | Situational analysis | 1 | Zhou Hong | [6 empty] | 2017-05-31 | 2017-10-31 | 2017-05-31 | Completed | September 2017 | Completed |  | Assessment report | Yes | Yes | Also includes 1.1.2, 1.3.7, 1.3.9, 1.4.1 and 1.2.1
|  |  |  | Identification and review of possible relevant EU experience |  |  | 7 | Birkholz, Lavigne, Mazzaferro, Suchomel, Skorpic, Steinmeyer, Zybkie | [6 empty] | August 2017 | Completed | September 2017 | Completed |  | Best practice report | Yes | Yes
|  |  |  | Panel discussion with stakeholders on the Identification phase | 1 | Zhou Hong | 5 | Birkholz, Mazzaferro, Suchomel, Skorpic, Steinmeyer | 20 |  |  |  | 2017-08-30 | - | 2017-08-30 | Completed | - | - |  | PPT, Panel Discussion Report | Yes | Yes | PPT received, Report
|  |  |  | International workshop in France | 1 | Zhou Hong | 9 | Rangus, Birkholz, Mazzaferro, Suchomel, Skorpic, Steinmeyer, Vleminckx, Thevenot, Vanhuysse | 4 |  |  | 2 | 2017-09-30 | 2017-10-31 | 2017-09-14 | Completed | September 2017 | Completed |  | PPTs and Workshop Report | Yes | Yes
| R5 | 1.4.2 | Relationship between social-economic development and the redistribution function of social security | Situational analysis | 1 | Li Shi | [6 empty] | 2017-09-30 | 2017-10-31 | August 2017 | Completed | September 2017 | Completed |  | PPT and Assessment report | Yes | Yes
|  |  |  | Panel discussion with stakeholders on the Identification phase | 1 | Li Shi |  |  | 20 |  |  |  | 2017-09-30 | - | August 2017 | Completed | - | - |  | Panel Discussion Report | Yes | Yes
|  |  |  | International workshop in France | 1 | Li Shi | 9 | Rangus, Birkholz, Mazzaferro, Suchomel, Skorpic, Steinmeyer, Vleminckx, Thevenot, Vanhuysse | 4 |  |  | 6 | 2017-09-30 | 2017-10-31 | August 2017 | Completed | September 2017 | Completed |  | PPTs, Workshop Report | Yes | Yes
|  |  |  | Dialogue and Study visit to Finland and Sweden |  |  |  |  | 4 |  |  |  | 2017-09-30 | 2017-10-31 | 2017-09-30 | Completed |  |  |  | Mission report | Yes | Yes
|  | 1.4.3 | Strategy of integrating social security system in urban and rural context also through the portability of social insurances | Pilot sites - Case Study in Sichuan (Luzhou) and Guangdong | 1 | Lin Yi - Sichuan Yue Jinglun - Guangdong | 2 | [5 empty] | 2017-05-31 | 2017-10-31 |  | On-going |  |  |  | Assessment report | Yes | No | Merged with 1.2.4 (Gender)